## Defect_Tracker
S No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Status | Remarks
1 | Backend | 2026-02-10 | Missing values causing pipeline failure | Sprint 1 | Backend | Logical | Applied interpolation & fill methods | Closed | Issue resolved
2 | Backend | 2026-02-12 | Incorrect datetime format | Sprint 1 | Backend | Logical | Converted to standard datetime format | Closed | Fixed
3 | Backend | 2026-02-15 | Lag feature producing null values | Sprint 2 | Backend | Logical | Dropped initial rows | Closed | Expected behavior
4 | Backend | 2026-02-20 | Model overfitting issue | Sprint 3 | Backend | Logical | Applied regularization | Closed | Improved performance
5 | Backend | 2026-02-28 | High RMSE in early model | Sprint 3 | Backend | Logical | Feature engineering improved | Closed | RMSE reduced
6 | Backend | 2026-03-03 | Forecast values inconsistency | Sprint 4 | Backend | Logical | Fixed prediction logic | Closed | Stable output
7 | Frontend | 2026-03-10 | Power BI data mismatch | Sprint 4 | Frontend | UI | Fixed column mapping | Closed | Dashboard correct
8 | Frontend | 2026-03-15 | Streamlit UI alignment issue | Sprint 4 | Frontend | UI | Adjusted layout | Closed | UI improved
9 | Backend | 2026-03-21 | CSV export formatting issue | Sprint 4 | Backend | Logical | Fixed formatting | Closed | Output correct
10 | Backend | 2026-03-27 | Monitoring alerts missing | Sprint 4 | Backend | Logical | Added threshold alerts | Open | Under improvement

## Sheet1
2026-02-10
2026-02-12
2026-02-15
2026-02-20
2026-02-28
2026-03-03
2026-03-10
2026-03-15
2026-03-21
2026-03-27